HepatoTwin- Weekly Action Plan

Meeting-by-Meeting Plan

| Meeting | Date | Task 1 (twin state + evidence) | Task 2 (optimizer + recipes) |
| --- | --- | --- | --- |
| 1 | Fri 21 Aug | NHANES data downloaded and linked; repository setup started | Recipe resources identified; database access/schema investigation started |
| 2 | Fri 28 Aug | EDA of CAP/steatosis; candidate feature list; preprocessing pipeline started | Read RecipeDB/FlavorDB/SpiceRx/DietRx papers; initial understanding of recipe schema and ingredient extraction |
| 3 | Thu 3 Sept | Train first baseline model using NHANES with train/test split | Build robust RecipeDB parser and extract recipe metadata, ingredients, cuisine, and preparation information |
| 4 | Fri 11 Sept | Compare baseline models and select initial patient-state prediction approach | Define a structured internal recipe representation and begin nutrient profiling of parsed recipes |
| 5 | Fri 18 Sept | Finalize initial predictive model and evaluate performance | Build recipe nutritional feature profiles: calories, macronutrients, fat-related variables, etc. |
| No meeting as it was mid-sem week | Fri 25 Sept | Light week: review model results and identify limitations | Light week: test parser and recipe representation on a larger recipe batch |
| 6 | Thu 1 Oct | Begin calibration and SHAP/explainability; draft evidence table from literature | Define recipe evaluation criteria: health alignment, cuisine compatibility, and practical feasibility |
| 7 | Fri 9 Oct | Complete initial evidence table and connect patient characteristics to nutritional objectives | Implement individual scoring functions for recipe-level criteria |
| 8 | Fri 16 Oct | Build Layer 3 logic: patient state → relevant nutritional priorities → priority levels | Implement patient-specific health alignment scoring for recipes |
| 9 | Fri 23 Oct | Integration checkpoint: model output → evidence layer → patient-specific objectives |  |
| 10 | Fri 30 Oct | Improve explainability: show why particular objectives were prioritized |  |
| 11 | Fri 6 Nov | Build patient/twin visualization and dashboard structure |  |
| 12 | Fri 13 Nov | Run model evaluation, sensitivity analysis, and evidence-layer testing |  |
| 13 | Fri 20 Nov | Freeze scope; consolidate results and prepare internal evaluation |  |
| 14 | Fri 27 Nov | Final debugging, documentation, and presentation preparation |  |